## Change Control Aug 2013
A | Cleanup Actions and Cosmetic Changes
1 | Deleted 'Test Custodian' from Nodes
2 | Deleted 'Test Harvest' from Nodes
3 | Renamed custodian 'Land Affairs_NSIF Administrator' to 'Land Affairs' - better for display and menus
4 | Retracted publications of node 'Department of Environmental Affairs' because it does not contain any meta-data.
B | Verification of Meta-Data Transfer
# | Issue or Question | Remedy or Answer | Status
1 | StatsSA: Question was raised in respect of the transfer of StatsSA meta-data from the original system. | StatsSA had 9 meta-data records in the old system, of which 7 do not contain any information (i.e. empty templates) and were not transferred. The other 2 are duplicates of the same (Enumerator Areas) meta-data, one in ISO/ SANS 1878 format, and one in FGDC - we have uploaded the ISO/ SANS 1878 copy. It is not published and will not show in searches because it contains spelling mistakes and is short of some information. 5 records could additionally not be imported - ESRI format (Census 2011). | Closed by SAEON NSIF to follow up with StatsSA
2 | NGI Status | 1590 meta-data records were provisionally published and are discoverable | Closed
3 | SANBI Status | 2 records, duplicates, contains very little information - not published | Closed
4 | City of Johannesburg | 11 records, 4 of which were published provisionally for the prototype as test, but apart from titles there isn't much information | Closed
5 | City of Tshwane | 11 records, none were published because the records contain titles only, no other meta-data | Closed
6 | Department of Environmental Affairs | Made private again, contains 1 record uploaded June 5th, 2013 that is empty. Not in original portal. | Closed
7 | Department of Water Affairs | Contains 8 records, of which 3 are duplicates. Some are complete, bit others not - as a consequence, we did not publish them and they will not show up in searches. | Closed by SAEON NSIF to follow up with DWA
8 | KZN DCOGTA | 1 meta-data record was transferred. It cannot be read by the portal because it is in ESRI meta-data format. The meta-data record contains valid information | Closed Consider extensions to read ESRI meta-data
9 | NGSI | 1 record, this has now been replaced by (1) above | Closed
10 | Premier's Office Eastern Cape - DOS | 1 record, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
11 | Premier's Office Eastern Cape - Base | 18 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
12 | Premier's Office Eastern Cape - DOA | 19 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
13 | Premier's Office Eastern Cape - DOED | 5 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
14 | Premier's Office Eastern Cape - DOEDE | 29 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
15 | Premier's Office Eastern Cape - DOH | 4 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
16 | Premier's Office Eastern Cape - DOPW | 1 record, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
17 | Premier's Office Eastern Cape - DOPW | 3 records, in ESRI Format - could not be imported | Closed Consider extensions to read ESRI meta-data
C | Extensions and Additions
# | Request | Remedy or Answer | Status
1 | View of Nodes in other Portals | This has been added - see | Closed
2 | Reporting extensions | This has been added - see | Closed
3 | Videos to assist with sign-off and training | This has been added - see | Closed